## Slide 1: State of Vermont Agency of Education eFinancePLUS Implementation Overview Presentation
Alicia Forward, PMP
PowerSchool Project Manager
April 23, 2018

## Slide 3: Agenda
Introductions and Overview
Implementation Methodology
Project Rollout Plan
and Sample Schedule
Next Steps

## Slide 4: Introductions and Overview
Vermont Agency of Education
Supervisory Unions
School Districts
PowerSchool
PowerSchool Project Manager
Alicia Forward
Supervisor, Professional Services
PowerSchool Project Sponsor
Lindsey Dorsey
Sr. Director of Professional Services
Vermont AOE Project Sponsor
Emily Byrne
Chief Financial Officer
Vermont Agency of Education Project Team
Tim Holland, IT Project Manager
Alena Berube, Compliance Proj. Mgr and Ed. Analyst
Sean Cousino, Education Finance Manager

## Slide 5: So Why Change? eFinancePLUS Advantages
Integrated—Accounting, payroll and human resources functionality is integrated in eFinancePLUS.
Modern—A modern web-based interface
Workflow-enabled—Paperless workflow for requisitioning, purchase order creation and HR onboarding.
Account Monitoring—Dynamic liability account monitoring and compliance for regulatory issues, including the Affordable Care Act.
Cognos—Standardized & dynamic/customizable report writing capabilities.

## Slide 6
The most critical reason for this change is…
Uniform Chart of Accounts
+
Reporting and Management of Metadata
Notes: Debbie info.

## Slide 7: 3 Key Takeaways
If you sign up for Rounds 1-4, you will receive unlimited Conversion Assistance for your Districts.
eFinancePLUS will allow you to make local level decisions and changes to your data tables. Your participation in the Business Process Reviews in May will help to guide these decisions.
Contact AOE.SSDDMS@vermont.gov for questions or support.

## Slide 8: Welcome to OnTrack
PowerSchool’s Proprietary Implementation Model
OnTrack acts as a guide through the 5 critical phases of your project
Project Managers have key deliverables which control the outcomes and minimize risk
Experienced Consultants provide “Best Practice” solutions for school districts.
Bring Software Live
  On Time
  Within Budget
  Following K-12 Best Practices

## Slide 9: Discovery
Business Process Reviews
Define Roadmap for the Project
Document Setup and Processing Decisions (i.e. UCOA)
End Result is Vermont Best Practices Guide
Begin Setting up Preconfigured Environment

## Slide 10: Planning
PowerSchool Project Manager is the SU/SDs point of Escalation
Lead Project Kickoff Call
Develop Implementation Schedule
Help Manage and Set Client Expectations
Conduct Regular Status Calls
Project Closeout Call
Keep Project on Time and within Budget
Deliverables
  Project Plan
  Scope of Work
  Project Budget
  Change Management Plan
  Risk Management Plan
  Communication Plan
  Project Closeout Report

## Slide 11: Preparation
System Installation
Load Preconfigured Environment
  State Chart of Accounts Structure
  State Codes
  State Tax Tables
Perform System Setup
  Follow Best Practice Recommendations

## Slide 12: Execution
Data Conversions
  Standard data conversion utilities within eFinancePLUS
  Conversion Files and Vermont Manuals on Customer Support Portal
  Consultant provides direct training to Supervisory Unions
  Supervisory Unions assist Districts with conversion process
Parallel Testing
  Consultant provides onsite training to Supervisory Unions
  Supervisory Unions assist Districts with parallel process

## Slide 13: Confirmation
Instructor Led “Train the Trainer”
Hands-On Training
Right-On-Time
Variety of Training Methods
  Onsite Instructor Led
  Seminar Series
  Office Hours
  Implementation Support
  eLearning embedded within the software
  Supervisory Union University

## Slide 14: Go Live & Post Live Support
Your Supervisory Union/Supervisory District
Vermont State Website and Team Email
  Email: aoe.ssddms@vermont.gov
  Website: http://education.vermont.gov/vermont-schools/school-finance/uniform-chart-accounts
PowerSchool Professional Services Support
  Office Hours
  Conversion Assistance
  Implementation Support
  Seminar Series
  eLearning
  Vermont Best Practices Guide
  Supervisory Union University
Helpdesk Support
  Submit Support Cases via web or phone
  Case Agents extremely knowledgeable
User Groups (SNUG) http://snugk12.org/
User Forum https://csforum.plus.powerschool.com

## Slide 15: Project Rollout Plan
Group: Up to 8 Supervisory Unions/Supervisory Districts
Round: Set of Groups implementing at the same time
Time: 6 month implementation for each Round

## Slide 16: Project Rollout Plan – All Rounds
Oct
2018
Round 1
Discovery
Oct
2019
Apr
2019
Apr
2018
July
2018
Jan
2019
July
2019
Round 2
Round 3
Round 4
Notes: Highlight Accelerated Round 1 Implementation at 4 months

## Slide 17: Implementation Timeline Overview
KICKOFF MEETING
OVERVIEWS & WORKSHOPS
SYSTEM CONFIG. & CONVERSION ORIENTATION
TRAINING FAM & HR/PY
PAYROLL PARALLEL AND CLIENT TESTING
LIVE CUTOVER
SUBMIT CLIENT CHECKLIST
PROJECT
REVIEW &
CLOSING
NEXT
PHASE

## Slide 18: Sample Project TimeLine

## Slide 19: Project Rollout Plan
All SUs wishing to opt-in should notify the SSDDMS project management team at AOE.SSDDMS@vermont.gov by the notification deadline specified in the table below, given the desired go-live date
Round | Go Live Date | Notification Deadline
1 | Oct 1, 2018 | Apr 27, 2018
2 | Jan 1, 2019 | May 31, 2018
3 | Apr 1, 2019 | Aug 31, 2018
4 | July 1, 2019 | Nov 30 2018

## Slide 20: What’s Next?
Task | Due Date
Attend Product Demo | Wednesday, April 25
Submit End User Agreement | Friday, April 27
Submit Cloud Setup Document | Friday, April 27
Schedule Installation | Monday, April 30
Attend Round 1 Kickoff Meeting | Thursday, May 3
Submit BPR Questionnaire | Friday, May 4
Identify Project Teams | Friday, May 4
Business Process Review: Session 1 | Tue-Thur, May 8-10
Business Process Review: Session 2 | Tue-Thur, May 15-17

## Slide 21: 3 Key Takeaways
If you sign up for Rounds 1-4, you will receive unlimited Conversion Assistance for your Districts.
eFinancePLUS will allow you to make local level decisions and changes to your data tables. Your participation in the Business Process Reviews in May will help to guide these decisions.
Contact AOE.SSDDMS@vermont.gov for questions or support.

## Slide 22: Questions?